## List
Fixed Lists |  | Fill in white cells only
Phases | Position | Region | Assign To | Editing Reason | Lisence Type | Project Types | تبدأ مرحلة الدراسة بعد توقيع العقد بـ .... أيام | تبدأ مرحلة التصميم بعد اعتماد مرحلة الدراسة بـ .... أيام | Holidays | Phase | Reply Reason | Allowance Times | Wieght (Reduction)
Studies | Head Dep | Riyadh | Client | Devlopment | Amanah | Residential |  |  | 2025-09-23 | Studies | Client Modification | 0
Design | Architect | Cairo | RCRC | Internally | TOD | Commercial | 10 | 5 | 2026-09-23 | Studies | Client Modification (Exceptional)
Technical | Quality Control |  | R.M | Client | KSR | Offices |  |  | 2027-09-23 | Studies | Technical Mistake | 1 | 15%
| Interior Designer |  | Design | Govermental | RCRC | Mixed-Use |  |  | 2028-09-23 | Studies | ...
| Draftsman |  | Technical | ... | SBF | High Rise |  |  | 2029-09-23 | Design | Client Modification | 2
| Engineering department head assistant |  | ... |  | Corridors | Culture |  |  | 2030-09-23 | Design | Client Modification (Exceptional)
| Team Leader |  |  |  | Wadi Hanifa | Religious |  |  | 2025-02-22 | Design | Technical Mistake | 1
| Structural Designer |  |  |  | Commercial Nerve | Resort |  |  | 2026-02-22 | Design | G.C Modification (Problems)
| Electrical Engineer |  |  |  | TOD + KSC | Educational |  |  | 2027-02-22 | Design | G.C Modification (Opinion)
| General Manager |  |  |  | Madinah | Interior |  |  | 2028-02-22 | Design | ...
[5 empty] | Qassim Amanah | Governmental |  |  | 2029-02-22 | Technical | Client Modification | 2
[5 empty] | Other | Others |  |  | 2030-02-22 | Technical | Client Modification (Exceptional)
[5 empty] | N/A | N/A |  |  | 2025-03-30 | Technical | Technical Mistake | 2
[9 empty] | 2025-03-31 | Technical | Technical Mistake (Design Dep) | 0
[9 empty] | 2025-04-01 | Technical | G.C Modification (Problems)
[9 empty] | 2026-03-20 | Technical | G.C Modification (Opinion)
[9 empty] | 2026-03-21 | Technical | Reviewing the G.C
[9 empty] | 2026-03-22 | Technical | ...
2027-03-10
2027-03-11
2027-03-12
2028-02-27
2028-02-28
2028-02-29
2029-02-15
2029-02-16
2029-02-17
2030-02-05
2030-02-06
2030-02-07
2025-06-06
2025-06-07
2025-06-08
2025-06-09
2026-05-27
2026-05-28
2026-05-29
2026-05-30
2027-05-17
2027-05-18
2027-05-19
2027-05-20
2028-05-05
2028-05-06
2028-05-07
2028-05-08
2029-04-24
2029-04-25
2029-04-26
2029-04-27
2030-04-14
2030-04-15
2030-04-16
2030-04-17

## Projects List
Project | Client | Contract Code | Signing Contract Date | BUA ¦ M2 | Lisence Type | Project Types | Project Requirment | Project Start Date ¦ Contract | Estimated End Date | Stu. Team Leader | Stu. Team Leader Working Percentage | Stu. Start Date ¦ Contract | Stu. Duration ¦ Contract | Stu. Allowed Modification (Times) | Stu. Modification days per time | Design Team Leader | Design Team Leader Working Percentage | Design. Start Date ¦ Contract | Design Duration ¦ Contract | Design Allowed Modification (Times) | Design Modification days per time | Tech. Team Leader | Tech. Team Leader Working Percentage | Tech. Start Date ¦ Contract | Tech. Duration ¦ Contract | Tech. Allowed Modification (Times) | Tech. Modification days per time | Stu. Cost % ¦ Contract Value | Design Cost % ¦ Contract Value | Tech. Cost % ¦ Contract Value | Contract Value | TeamLeader1 | TeamLeader2 | TeamLeader3
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35
Projects List | Projects List |  | Fill in white cells only | [6 empty] | Study Phase | [5 empty] | Design Phase | [5 empty] | Technical Phase
Project | Client | Contract Code | Signing Contract Date | BUA ¦ M2 | Lisence Type | Project Types | Project Requirment | Project Start Date ¦ Contract | Estimated End Date | Stu. Team Leader | Stu. Team Leader Working Percentage | Stu. Start Date ¦ Contract | Stu. Duration ¦ Contract | Stu. Allowed Modification (Times) | Stu. Modification days per time | Design Team Leader | Design Team Leader Working Percentage | Design. Start Date ¦ Contract | Design Duration ¦ Contract | Design Allowed Modification (Times) | Design Modification days per time | Tech. Team Leader | Tech. Team Leader Working Percentage | Tech. Start Date ¦ Contract | Tech. Duration ¦ Contract | Tech. Allowed Modification (Times) | Tech. Modification days per time | Stu. Cost % ¦ Contract Value | Design Cost % ¦ Contract Value | Tech. Cost % ¦ Contract Value | Contract Value | TeamLeader1 | TeamLeader2 | TeamLeader3
Park View | MOBTAKERON REAL ESTATE COMPANY | REF.02.383 | 2024-10-09 | 7394 | TOD | Residential | https://docs.google.com/spreadsheets/d/12b3TkOQbtVg1zjgbLLWYiSykhTxYcu7Vy4ZGWosqG5E/edit?usp=sharing | 2024-10-23 | 2025-08-27 |  | 25% | 2024-10-23 | 15 | 0 | 0 | Riyadh Almaghrabi | 25% | 2024-11-20 | 70 | 2 | 10 |  | 0% | 2025-03-26 | 85 | 2 | 10 | 15% | 45% | 40% | 3500000 | 0 | 8603.9425 | 0
Details | DETAILS REAL ESTATE COMPANY | REF.02.387 | 2024-12-09 | 38881.2 | Corridors | Mixed-Use |  | 2024-12-23 | 2025-09-22 |  | 25% | 2024-12-23 | 15 | 0 | 0 | Riyadh Almaghrabi | 30% | 2025-01-20 | 70 | 2 | 10 |  | 0% | 2025-05-29 | 60 | 2 | 10 | 15% | 45% | 40% | 1500000 | 0 | 10324.731 | 0
Jevan Tower | MR. BANDAR BIN MOHAMMED AL MUSIRYIE | REF.02.366 | 2024-08-13 | 24743.6 | TOD | Residential |  | 2024-08-27 | 2025-05-25 |  | 25% | 2024-08-27 | 15 | 0 | 0 | Ghadeer AlAmoudi |  | 2024-09-24 | 70 | 2 | 10 |  | 100% | 2025-01-28 | 60 | 2 | 10 | 15% | 45% | 40% | 1500000 | 0 | 0 | 0
Al Hamra Mixed Use TOD Project | Rabwa Al Omran Contracting Company | REF.02.406 | 2025-05-29 | 29292 | TOD | Mixed-Use |  | 2025-06-16 | 2026-03-11 |  | 25% | 2025-06-16 | 15 | 0 | 0 | Riyadh Almaghrabi | 30% | 2025-07-14 | 70 | 2 | 10 |  | 0% | 2025-11-18 | 60 | 2 | 10 | 15% | 45% | 40% | 1500000 | 0 | 10324.731 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 | [5 empty] | 0 | [7 empty] | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 | [5 empty] | 0 | [7 empty] | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 | [5 empty] | 0 | [7 empty] | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 | [5 empty] | 0 | [7 empty] | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 | [5 empty] | 0 | [7 empty] | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 | [5 empty] | 0 | [7 empty] | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 | [5 empty] | 0 | [7 empty] | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 | [5 empty] | 0 | [7 empty] | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 | [5 empty] | 0 | [7 empty] | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 | [5 empty] | 0 | [7 empty] | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 | [5 empty] | 0 | [7 empty] | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 | [5 empty] | 0 | [7 empty] | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 | [5 empty] | 0 | [7 empty] | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 | [5 empty] | 0 | [7 empty] | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 | [5 empty] | 0 | [7 empty] | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 | [5 empty] | 0 | [7 empty] | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 | [5 empty] | 0 | [7 empty] | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 | [5 empty] | 0 | [7 empty] | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 | [5 empty] | 0 | [7 empty] | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 | [5 empty] | 0 | [7 empty] | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 | [5 empty] | 0 | [7 empty] | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 | [5 empty] | 0 | [7 empty] | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 | [5 empty] | 0 | [7 empty] | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 | [5 empty] | 0 | [7 empty] | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 | [5 empty] | 0 | [7 empty] | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 | [5 empty] | 0 | [7 empty] | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 | [5 empty] | 0 | [7 empty] | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 | [5 empty] | 0 | [7 empty] | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 | [5 empty] | 0 | [7 empty] | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 | [5 empty] | 0 | [7 empty] | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 | [5 empty] | 0 | [7 empty] | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 | [5 empty] | 0 | [7 empty] | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 | [5 empty] | 0 | [7 empty] | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 | [5 empty] | 0 | [7 empty] | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 | [5 empty] | 0 | [7 empty] | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 | [5 empty] | 0 | [7 empty] | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 | [5 empty] | 0 | [7 empty] | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 | [5 empty] | 0 | [7 empty] | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 | [5 empty] | 0 | [7 empty] | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 | [5 empty] | 0 | [7 empty] | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 | [5 empty] | 0 | [7 empty] | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 | [5 empty] | 0 | [7 empty] | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 | [5 empty] | 0 | [7 empty] | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 | [5 empty] | 0 | [7 empty] | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 | [5 empty] | 0 | [7 empty] | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 | [5 empty] | 0 | [7 empty] | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 | [5 empty] | 0 | [7 empty] | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 | [5 empty] | 0 | [7 empty] | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 | [5 empty] | 0 | [7 empty] | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 | [5 empty] | 0 | [7 empty] | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 | [5 empty] | 0 | [7 empty] | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 | [5 empty] | 0 | [7 empty] | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 | [5 empty] | 0 | [7 empty] | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 | [5 empty] | 0 | [7 empty] | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 | [5 empty] | 0 | [7 empty] | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 | [5 empty] | 0 | [7 empty] | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 | [5 empty] | 0 | [7 empty] | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 | [5 empty] | 0 | [7 empty] | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 | [5 empty] | 0 | [7 empty] | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 | [5 empty] | 0 | [7 empty] | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 | [5 empty] | 0 | [7 empty] | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 | [5 empty] | 0 | [7 empty] | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 | [5 empty] | 0 | [7 empty] | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 | [5 empty] | 0 | [7 empty] | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 | [5 empty] | 0 | [7 empty] | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 | [5 empty] | 0 | [7 empty] | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 | [5 empty] | 0 | [7 empty] | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 | [5 empty] | 0 | [7 empty] | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 |  | 2 | 10 |  |  | 0 | [7 empty] | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 |  | 2 | 10 |  |  | 0 | [7 empty] | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 |  | 2 | 10 |  |  | 0 | [7 empty] | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 |  | 2 | 10 |  |  | 0 | [7 empty] | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 |  | 2 | 10 |  |  | 0 |  | 2 | 10 |  |  |  |  | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 |  | 2 | 10 |  |  | 0 |  | 2 | 10 |  |  |  |  | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 |  | 2 | 10 |  |  | 0 |  | 2 | 10 |  |  |  |  | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 |  | 2 | 10 |  |  | 0 |  | 2 | 10 |  |  |  |  | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 |  | 2 | 10 |  |  | 0 |  | 2 | 10 |  |  |  |  | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 |  | 2 | 10 |  |  | 0 |  | 2 | 10 |  |  |  |  | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 |  | 2 | 10 |  |  | 0 |  | 2 | 10 |  |  |  |  | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 |  | 2 | 10 |  |  | 0 |  | 2 | 10 |  |  |  |  | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 |  | 2 | 10 |  |  | 0 |  | 2 | 10 |  |  |  |  | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 |  | 2 | 10 |  |  | 0 |  | 2 | 10 |  |  |  |  | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 |  | 2 | 10 |  |  | 0 |  | 2 | 10 |  |  |  |  | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 |  | 2 | 10 |  |  | 0 |  | 2 | 10 |  |  |  |  | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 |  | 2 | 10 |  |  | 0 |  | 2 | 10 |  |  |  |  | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 |  | 2 | 10 |  |  | 0 |  | 2 | 10 |  |  |  |  | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 |  | 2 | 10 |  |  | 0 |  | 2 | 10 |  |  |  |  | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 |  | 2 | 10 |  |  | 0 |  | 2 | 10 |  |  |  |  | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 |  | 2 | 10 |  |  | 0 |  | 2 | 10 |  |  |  |  | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 |  | 2 | 10 |  |  | 0 |  | 2 | 10 |  |  |  |  | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 |  | 2 | 10 |  |  | 0 |  | 2 | 10 |  |  |  |  | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 |  | 2 | 10 |  |  | 0 |  | 2 | 10 |  |  |  |  | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 |  | 2 | 10 |  |  | 0 |  | 2 | 10 |  |  |  |  | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 |  | 2 | 10 |  |  | 0 |  | 2 | 10 |  |  |  |  | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 |  | 2 | 10 |  |  | 0 |  | 2 | 10 |  |  |  |  | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 |  | 2 | 10 |  |  | 0 |  | 2 | 10 |  |  |  |  | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 |  | 2 | 10 |  |  | 0 |  | 2 | 10 |  |  |  |  | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 |  | 2 | 10 |  |  | 0 |  | 2 | 10 |  |  |  |  | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 |  | 2 | 10 |  |  | 0 |  | 2 | 10 |  |  |  |  | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 |  | 2 | 10 |  |  | 0 |  | 2 | 10 |  |  |  |  | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 |  | 2 | 10 |  |  | 0 |  | 2 | 10 |  |  |  |  | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 |  | 2 | 10 |  |  | 0 |  | 2 | 10 |  |  |  |  | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 |  | 2 | 10 |  |  | 0 |  | 2 | 10 |  |  |  |  | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 |  | 2 | 10 |  |  | 0 |  | 2 | 10 |  |  |  |  | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 |  | 2 | 10 |  |  | 0 |  | 2 | 10 |  |  |  |  | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 |  | 2 | 10 |  |  | 0 |  | 2 | 10 |  |  |  |  | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 |  | 2 | 10 |  |  | 0 |  | 2 | 10 |  |  |  |  | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 |  | 2 | 10 |  |  | 0 |  | 2 | 10 |  |  |  |  | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 |  | 2 | 10 |  |  | 0 |  | 2 | 10 |  |  |  |  | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 |  | 2 | 10 |  |  | 0 |  | 2 | 10 |  |  |  |  | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 |  | 2 | 10 |  |  | 0 |  | 2 | 10 |  |  |  |  | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 |  | 2 | 10 |  |  | 0 |  | 2 | 10 |  |  |  |  | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 |  | 2 | 10 |  |  | 0 |  | 2 | 10 |  |  |  |  | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 |  | 2 | 10 |  |  | 0 |  | 2 | 10 |  |  |  |  | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 |  | 2 | 10 |  |  | 0 |  | 2 | 10 |  |  |  |  | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 |  | 2 | 10 |  |  | 0 |  | 2 | 10 |  |  |  |  | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 |  | 2 | 10 |  |  | 0 |  | 2 | 10 |  |  |  |  | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 |  | 2 | 10 |  |  | 0 |  | 2 | 10 |  |  |  |  | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 |  | 2 | 10 |  |  | 0 |  | 2 | 10 |  |  |  |  | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 |  | 2 | 10 |  |  | 0 |  | 2 | 10 |  |  |  |  | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 |  | 2 | 10 |  |  | 0 |  | 2 | 10 |  |  |  |  | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 |  | 2 | 10 |  |  | 0 |  | 2 | 10 |  |  |  |  | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 |  | 2 | 10 |  |  | 0 |  | 2 | 10 |  |  |  |  | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 |  | 2 | 10 |  |  | 0 |  | 2 | 10 |  |  |  |  | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 |  | 2 | 10 |  |  | 0 |  | 2 | 10 |  |  |  |  | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 |  | 2 | 10 |  |  | 0 |  | 2 | 10 |  |  |  |  | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 |  | 2 | 10 |  |  | 0 |  | 2 | 10 |  |  |  |  | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 |  | 2 | 10 |  |  | 0 |  | 2 | 10 |  |  |  |  | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 |  | 2 | 10 |  |  | 0 |  | 2 | 10 |  |  |  |  | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 |  | 2 | 10 |  |  | 0 |  | 2 | 10 |  |  |  |  | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 |  | 2 | 10 |  |  | 0 |  | 2 | 10 |  |  |  |  | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 |  | 2 | 10 |  |  | 0 |  | 2 | 10 |  |  |  |  | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 |  | 2 | 10 |  |  | 0 |  | 2 | 10 |  |  |  |  | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 |  | 2 | 10 |  |  | 0 |  | 2 | 10 |  |  |  |  | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 |  | 2 | 10 |  |  | 0 |  | 2 | 10 |  |  |  |  | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 |  | 2 | 10 |  |  | 0 |  | 2 | 10 |  |  |  |  | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 |  | 2 | 10 |  |  | 0 |  | 2 | 10 |  |  |  |  | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 |  | 2 | 10 |  |  | 0 |  | 2 | 10 |  |  |  |  | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 |  | 2 | 10 |  |  | 0 |  | 2 | 10 |  |  |  |  | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 |  | 2 | 10 |  |  | 0 |  | 2 | 10 |  |  |  |  | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 |  | 2 | 10 |  |  | 0 |  | 2 | 10 |  |  |  |  | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 |  | 2 | 10 |  |  | 0 |  | 2 | 10 |  |  |  |  | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 |  | 2 | 10 |  |  | 0 |  | 2 | 10 |  |  |  |  | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 |  | 2 | 10 |  |  | 0 |  | 2 | 10 |  |  |  |  | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 |  | 2 | 10 |  |  | 0 |  | 2 | 10 |  |  |  |  | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 |  | 2 | 10 |  |  | 0 |  | 2 | 10 |  |  |  |  | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 |  | 2 | 10 |  |  | 0 |  | 2 | 10 |  |  |  |  | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 |  | 2 | 10 |  |  | 0 |  | 2 | 10 |  |  |  |  | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 |  | 2 | 10 |  |  | 0 |  | 2 | 10 |  |  |  |  | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 |  | 2 | 10 |  |  | 0 |  | 2 | 10 |  |  |  |  | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 |  | 2 | 10 |  |  | 0 |  | 2 | 10 |  |  |  |  | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 |  | 2 | 10 |  |  | 0 |  | 2 | 10 |  |  |  |  | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 |  | 2 | 10 |  |  | 0 |  | 2 | 10 |  |  |  |  | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 |  | 2 | 10 |  |  | 0 |  | 2 | 10 |  |  |  |  | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 |  | 2 | 10 |  |  | 0 |  | 2 | 10 |  |  |  |  | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 |  | 2 | 10 |  |  | 0 |  | 2 | 10 |  |  |  |  | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 |  | 2 | 10 |  |  | 0 |  | 2 | 10 |  |  |  |  | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 |  | 2 | 10 |  |  | 0 |  | 2 | 10 |  |  |  |  | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 |  | 2 | 10 |  |  | 0 |  | 2 | 10 |  |  |  |  | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 |  | 2 | 10 |  |  | 0 |  | 2 | 10 |  |  |  |  | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 |  | 2 | 10 |  |  | 0 |  | 2 | 10 |  |  |  |  | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 |  | 2 | 10 |  |  | 0 |  | 2 | 10 |  |  |  |  | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 |  | 2 | 10 |  |  | 0 |  | 2 | 10 |  |  |  |  | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 |  | 2 | 10 |  |  | 0 |  | 2 | 10 |  |  |  |  | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 |  | 2 | 10 |  |  | 0 |  | 2 | 10 |  |  |  |  | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 |  | 2 | 10 |  |  | 0 |  | 2 | 10 |  |  |  |  | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 |  | 2 | 10 |  |  | 0 |  | 2 | 10 |  |  |  |  | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 |  | 2 | 10 |  |  | 0 |  | 2 | 10 |  |  |  |  | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 |  | 2 | 10 |  |  | 0 |  | 2 | 10 |  |  |  |  | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 |  | 2 | 10 |  |  | 0 |  | 2 | 10 |  |  |  |  | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 |  | 2 | 10 |  |  | 0 |  | 2 | 10 |  |  |  |  | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 |  | 2 | 10 |  |  | 0 |  | 2 | 10 |  |  |  |  | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 |  | 2 | 10 |  |  | 0 |  | 2 | 10 |  |  |  |  | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 |  | 2 | 10 |  |  | 0 |  | 2 | 10 |  |  |  |  | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 |  | 2 | 10 |  |  | 0 |  | 2 | 10 |  |  |  |  | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 |  | 2 | 10 |  |  | 0 |  | 2 | 10 |  |  |  |  | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 |  | 2 | 10 |  |  | 0 |  | 2 | 10 |  |  |  |  | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 |  | 2 | 10 |  |  | 0 |  | 2 | 10 |  |  |  |  | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 |  | 2 | 10 |  |  | 0 |  | 2 | 10 |  |  |  |  | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 |  | 2 | 10 |  |  | 0 |  | 2 | 10 |  |  |  |  | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 |  | 2 | 10 |  |  | 0 |  | 2 | 10 |  |  |  |  | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 |  | 2 | 10 |  |  | 0 |  | 2 | 10 |  |  |  |  | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 |  | 2 | 10 |  |  | 0 |  | 2 | 10 |  |  |  |  | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 |  | 2 | 10 |  |  | 0 |  | 2 | 10 |  |  |  |  | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 |  | 2 | 10 |  |  | 0 |  | 2 | 10 |  |  |  |  | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 |  | 2 | 10 |  |  | 0 |  | 2 | 10 |  |  |  |  | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 |  | 2 | 10 |  |  | 0 |  | 2 | 10 |  |  |  |  | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 |  | 2 | 10 |  |  | 0 |  | 2 | 10 |  |  |  |  | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 |  | 2 | 10 |  |  | 0 |  | 2 | 10 |  |  |  |  | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 |  | 2 | 10 |  |  | 0 |  | 2 | 10 |  |  |  |  | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 |  | 2 | 10 |  |  | 0 |  | 2 | 10 |  |  |  |  | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 |  | 2 | 10 |  |  | 0 |  | 2 | 10 |  |  |  |  | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 |  | 2 | 10 |  |  | 0 |  | 2 | 10 |  |  |  |  | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 |  | 2 | 10 |  |  | 0 |  | 2 | 10 |  |  |  |  | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 |  | 2 | 10 |  |  | 0 |  | 2 | 10 |  |  |  |  | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 |  | 2 | 10 |  |  | 0 |  | 2 | 10 |  |  |  |  | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0 | [5 empty] | 0 |  | 2 | 10 |  |  | 0 |  | 2 | 10 |  |  |  |  | 0 | 0 | 0
Formulas:
Project Start Date ¦ Contract = IF(الجدول1[[#This Row],[Signing Contract Date]]=0,0,WORKDAY.INTL(الجدول1[[#This Row],[Signing Contract Date]],List!$J4,7,List!$M3:M100))
Estimated End Date = IF([Tech. Duration ¦ Contract]=0,0,WORKDAY.INTL([Tech. Start Date ¦ Contract],[Tech. Duration ¦ Contract]+([Tech. Allowed Modification (Times)]*[Tech. Modification days per time]),7,List!$M3:M100))
Stu. Start Date ¦ Contract = الجدول1[[#This Row],[Project Start Date ¦ Contract]]
Design. Start Date ¦ Contract = IF([Stu. Start Date ¦ Contract]=0,0, WORKDAY.INTL( WORKDAY.INTL([Stu. Start Date ¦ Contract],[Stu. Duration ¦ Contract]+([Stu. Allowed Modification (Times)]*[Stu. Modification days per time]),7,List!$M3:M100),List!$K4,7,List!$M3:M100))
Tech. Start Date ¦ Contract = IF([Design. Start Date ¦ Contract]=0,0,WORKDAY.INTL([Design. Start Date ¦ Contract],[Design Duration ¦ Contract]+([Design Allowed Modification (Times)]*[Design Modification days per time]),7,List!$M3:M100))

## KPI
| Fill in white cells only | KPIs Data
KPIs Item | Wieght | Project Allowance Delay (Days) | Wieght for 1 Day Delay (Reduction) | Level | Max | Min
Employee Delay | 50% | 3 | 1% | A | 100% | 81%
Reply Reason | 50% |  |  | B | 80% | 61%
| 100% |  |  | C | 60% | 41%
|  |  |  | D | 40% | 21%
|  |  |  | E | 20% | 1%
|  |  |  | F | 0%

## Tasks
|  | Tasks Durations (days) | Fill in white cells only. Don't Leave Blank Rows. |  | Check Phases Durations in Project List
Code | Phase | Task Discribtion | Task for: |  | Park View | Details | Jevan Tower | Al Hamra Mixed Use TOD Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Studies Working on - Studies | Studies | Working on - Studies | Internal | Internal1 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
Studies ReWorking - Studies | Studies | ReWorking - Studies | Internal | Internal2 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
Studies ReWorking - Studies (VO) | Studies | ReWorking - Studies (VO) | Internal | Internal3 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
Studies Review and Comment - Studies | Studies | Review and Comment - Studies | Client | Client1 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
Studies Approved - Studies | Studies | Approved - Studies | Client | Client2 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
| Design | Working on - Design 25% | Internal | Internal4 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20
Design ReWorking - Design 25% | Design | ReWorking - Design 25% | Internal | Internal5 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
| Design | ReWorking - Design 25% (VO) | Internal | Internal6 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
| Design | Review and Comment - Design 25% | Client | Client3 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
| Design | Approved - Design 25% | Client | Client4 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Design Working on - Design 50% | Design | Working on - Design 50% | Internal | Internal7 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20
| Design | ReWorking - Design 50% | Internal | Internal8 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
Design ReWorking - Design 50% (VO) | Design | ReWorking - Design 50% (VO) | Internal | Internal9 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
Design Review and Comment - Design 50% | Design | Review and Comment - Design 50% | Client | Client5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
Design Approved - Design 50% | Design | Approved - Design 50% | Client | Client6 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Design | Working on - Design 75% | Internal | Internal10 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20
| Design | ReWorking - Design 75% | Internal | Internal11 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
| Design | ReWorking - Design 75% (VO) | Internal | Internal12 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
| Design | Review and Comment - Design 75% | Client | Client7 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
| Design | Approved - Design 75% | Client | Client8 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Design | Working on - Design 100% | Internal | Internal13 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20
| Design | ReWorking - Design 100% | Internal | Internal14 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
| Design | ReWorking - Design 100% (VO) | Internal | Internal15 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
| Design | Review and Comment - Design 100% | Client | Client9 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
| Design | Approved - Design 100% | Client | Client10 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Design | Issuing 1st to G.C | Government | Government1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Design | Reissuing 1st to G.C | Government | Government2 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
| Design | Approval 1st - License | Government | Government3 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90
| Design | Coordinate with Out-source | Client | Client11 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
| Technical | Handover | Internal | Internal16 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
| Technical | Working on - Development | Internal | Internal17 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20
| Technical | ReWorking - Development | Internal | Internal18 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
| Technical | ReWorking - Development (VO) | Internal | Internal19 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
| Technical | Review and Comment - Development | Client | Client12 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
| Technical | Approval - Development | Client | Client13 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Technical Working on - License | Technical | Working on - License | Internal | Internal20 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
| Technical | Issuing the license - R.M | Government | Government4 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
| Technical | Reworking & Issuing the license - R.M | Internal | Internal21 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
| Technical | Approval the License - R.M | Government | Government5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Technical | Working on - D.D | Internal | Internal22 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60
Technical ReWorking - D.D (VO) | Technical | ReWorking - D.D (VO) | Internal | Internal23 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
| Technical | Review and Comment - DD | Client | Client14 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
| Technical | Approval - DD | Client | Client15 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Technical | Working on 01 - BOQ | Internal | Internal24 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
| Technical | ReWorking - BOQ (VO) | Internal | Internal25 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
| Technical | Review and Comment - BOQ | Client | Client16 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
| Technical | Approval - BOQ | Client | Client17 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Technical | Coordinate with Out-source. | Client | Client18 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## External Tasks (hidden)
Code | Phase | Client Tasks |  | Code | Phase | Government Tasks
Studies Review and Comment - Studies | Studies | Review and Comment - Studies | 1 | Design Issuing 1st to G.C | Design | Issuing 1st to G.C
Studies Approved - Studies | Studies | Approved - Studies | 2 | Design Reissuing 1st to G.C | Design | Reissuing 1st to G.C
Design Review and Comment - Design 25% | Design | Review and Comment - Design 25% | 3 | Design Approval 1st - License | Design | Approval 1st - License
Design Approved - Design 25% | Design | Approved - Design 25% | 4 | Technical Issuing the license - R.M | Technical | Issuing the license - R.M
Design Review and Comment - Design 50% | Design | Review and Comment - Design 50% | 5 | Technical Approval the License - R.M | Technical | Approval the License - R.M
Design Approved - Design 50% | Design | Approved - Design 50% | 6
Design Review and Comment - Design 75% | Design | Review and Comment - Design 75% | 7
Design Approved - Design 75% | Design | Approved - Design 75% | 8
Design Review and Comment - Design 100% | Design | Review and Comment - Design 100% | 9
Design Approved - Design 100% | Design | Approved - Design 100% | 10
Design Coordinate with Out-source | Design | Coordinate with Out-source | 11
Technical Review and Comment - Development | Technical | Review and Comment - Development | 12
Technical Approval - Development | Technical | Approval - Development | 13
Technical Review and Comment - DD | Technical | Review and Comment - DD | 14
Technical Approval - DD | Technical | Approval - DD | 15
Technical Review and Comment - BOQ | Technical | Review and Comment - BOQ | 16
Technical Approval - BOQ | Technical | Approval - BOQ | 17
Technical Coordinate with Out-source. | Technical | Coordinate with Out-source. | 18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99

## Employees
|  |  | Employees Data |  | Fill in white cells only
| Phase | Employee | Position | Emoployee's Cost ¦ Monthly | Email | Region
Design | Design | Ahmed AL-Attas |  | 27792.61 |  | Riyadh | Design Ahmed AL-Attas | Abderrahmane Boukaiss | a.boukaiss@cleardes.com
Design Head Dep | Design | Younes Al-Ammar | Head Dep | 41317.05 |  | Riyadh | Design Younes Al-Ammar | Salman Fahad Mulhim | s.almulhim@cleardes.com
Design | Design | Abdulaziz Alsaqqaf |  | 28768.4 |  | Riyadh | Design Abdulaziz Alsaqqaf | Aamir Shahbaz | aamir.shahbaz@cleardes.com
Design | Design | Ghadeer AlAmoudi |  | 34055.38 |  | Riyadh | Design Ghadeer AlAmoudi | Abdul Rahman | a.rahman@cleardes.com
Design | Design | Riyadh Almaghrabi |  | 34415.77 |  | Riyadh | Design Riyadh Almaghrabi | Abdulaziz Al Saggaf | abdulaziz@cleardes.com
Design | Design | Rakan Arrabea |  | 25938.91 |  | Riyadh | Design Rakan Arrabea | Abdulmohsin Bin Madhi | binmadhi@cleardes.com
| Design | Aljawharah Aldahmash |  | 26243.78 |  | Riyadh | Design Aljawharah Aldahmash | Ahmed Al.Attas | alattas@cleardes.com
| Design | Majed Al-Shadokhi |  | 6615.93 |  | Riyadh | Design Majed Al-Shadokhi | Ahmed Sharara | a.sharara@cleardes.com
Design | Design | Mohamed shaldoum |  | 20381.08 |  | Riyadh | Design Mohamed shaldoum | Al Jawharah Aldahmash | a.aldahmash@cleardes.com
Design | Design | ahmed sharara |  | 31760.09 |  | Riyadh | Design ahmed sharara | Badr Mohammed Alrubie | b.alrubie@cleardes.com
Design | Design | Bader Alribi |  | 24424.21 |  | Riyadh | Design Bader Alribi | Ghadeer Alamoudi | ghadeer@cleardes.com
Design | Design | Ummer Abdulmajeed |  | 17278.61 |  | Riyadh | Design Ummer Abdulmajeed | Islam Mohammed | islam@cleardes.com
Design | Design | Muath Jumayah |  | 15961.33 |  | Riyadh | Design Muath Jumayah | Jayson Bautista | jayson@cleardes.com
Design | Design | Basem Osman |  | 16742.4 |  | Riyadh | Design Basem Osman | Mohammad Al Sharabi | m.alsharabi@cleardes.com
Design | Design | Abdullah Alrahmah |  | 13712.58 |  | Riyadh | Design Abdullah Alrahmah | Mohammed Al Attar | attar@cleardes.com
Design | Design | Nouf shahbal |  | 9386.74 |  | Riyadh | Design Nouf shahbal
| Design | Nawaf Al Turaif |  | 4469.99 |  | Riyadh | Design Nawaf Al Turaif | Muhamed Faisal | m.faisal@cleardes.com
Studies | Studies | Salman Mulhim |  | 26427.72 |  | Riyadh | Studies Salman Mulhim
Studies Head Dep | Studies | Abdulrahman Bukees | Head Dep | 31573.65 |  | Riyadh | Studies Abdulrahman Bukees
Studies | Studies | Omar Nada |  | 24207.31 |  | Riyadh | Studies Omar Nada
| Studies | Ahmed Mahmoud |  | 11268.92 |  | Riyadh | Studies Ahmed Mahmoud | Muna` Ahmed | muna@cleardes.com
Studies | Studies | Satam Bahtab |  | 11280.2 |  | Riyadh | Studies Satam Bahtab | Oday Bassam | oday@cleardes.com
Studies | Studies | Muhammad Alsharabi |  | 14846.36 |  | Riyadh | Studies Muhammad Alsharabi | Omar Majdi | o.majdi@cleardes.com
Technical Head Dep | Technical | Abdulmahsen Madhi | Head Dep | 39495.37 |  | Riyadh | Technical Abdulmahsen Madhi | Omer Osman | omer.osman@cleardes.com
Technical | Technical | Jayson Bautista |  | 26464.02 |  | Riyadh | Technical Jayson Bautista | Rakan Arrabea | r.arrabea@cleardes.com
Technical | Technical | Mohammed Al-Attar |  | 27163.99 |  | Riyadh | Technical Mohammed Al-Attar | Riyadh Al Maghrabi | riyadh@cleardes.com
Technical | Technical | Odai Souliman |  | 30473.57 |  | Riyadh | Technical Odai Souliman | Yonas ALammar | yonas@cleardes.com
Technical | Technical | Omar Darrar |  | 24338.07 |  | Riyadh | Technical Omar Darrar
Technical | Technical | Aamir Ahmad |  | 23556.06 |  | Riyadh | Technical Aamir Ahmad
Technical | Technical | Islam Abdelati |  | 32079.96 |  | Riyadh | Technical Islam Abdelati
| Technical | Muna Mubarak |  | 16940.3 |  | Riyadh | Technical Muna Mubarak
Technical | Technical | Abdulrahman Mohammed |  | 31412.61 |  | Riyadh | Technical Abdulrahman Mohammed
Technical | Technical | Ahmed Marrwa Marrwa |  | 39497.47 |  | Riyadh | Technical Ahmed Marrwa Marrwa
Technical | Technical | Abdulelah Alforih |  | 12551.97 |  | Riyadh | Technical Abdulelah Alforih
Technical | Technical | Abdulaziz Aljanobi |  | 9821.61 |  | Riyadh | Technical Abdulaziz Aljanobi
| Technical | Egypt |  |  |  | Cairo | Technical Egypt

## HeadDep (hidden)
Studies | Head Dep | 31573.65
Design | Head Dep | 41317.05
Technical | Head Dep | 39495.37